## Sheet1
Risk ID | Asset | Threat | Vulnerability | Likelihood | Impact = (1-5) | Risk Score = (likelihood *Impact) | Risk Level | Mitigation | Owner
R001 | Employee Laptop | Malware Infection | No antivirus installed on endpoints | 4 | 5 | 20 | High | Install enterprise-grade endpoint protection and enforce regular upgrade | IT Team
R002 | Cloud Storage | Data Breach | Weak access control and no multi-factor authentication | 3 | 5 | 15 | High | Implement MFA and role-based-access control (RBAC) | Security Team
R003 | Email System | Phishing Attach | Lack of user security awareness training | 4 | 4 | 16 | High | Conduct regular phishing simulation and security awareness training | HR/IT
R004 | Web Server | DDoS Attack | No traffic filtering or DDoS mitigation control | 3 | 4 | 12 | Medium | Deploy firewall and DDoS protection services | Network Team
R005 | Datebase | Unathorised Access | Default credentials and Weak password | 2 | 5 | 10 | Medium | Enable MFA and enforce strong password policies | IT Team
R006 | User Accounts | Brute Force Attack | No MFA and weak passwords | 4 | 4 | 16 | High | Enable MFA and enforce strong password policies | IT Team
R007 | Network Router | Unathorised Access | Open ports | 3 | 4 | 12 | Medium | Harden Configuration and disable unsed servives firewall rules | Network Team
R008 | Backup systems | Data Loss | Backup not regularly tested or verified | 3 | 5 | 15 | High | Schedule regular backup tests | IT Team
R009 | HR System | Insider Threat | Excess user Privileges and lack of monitoring | 2 | 5 | 10 | Medium | Implement least principle access , activity monitoring and validation procedure | HR/IT
R010 | Website | SQL Injection Attack | Poor input validation and lack of secure coding practices | 3 | 5 | 15 | High | Implement input validation, parameterized queries, and web application firewall | Dev Team